Application for a grant under call for proposals 2006/C 236/07 concerning information measures on the common agricultural policy

Action 2 –  Conferences and seminars, in particular, in rural zones
Grant Agreement in application of Council Regulation N°814/2000 on information measures relating to the common agricultural policy

Project title: “Future perspectives of rural development: comparing different European scenarios”

Objectives and actions:

The project will consist in the organization of a seminar set out in three days, and taking place in ( Hungary or other East Europe country) focused on the issues of EU rural development policies, in the light of the fundamental reformation of the first pillar of the Common Agricultural Policy, with reference to the policies and the local initiatives of the involved partners.

The seminar, besides illustrating the main aspects of the European legislation on rural development related to the phase 2007/2013, will represent an opportunity of comparison useful to deepen approaches and methods in the management of rural development policies, also with reference to the problems emerging from the east Europe countries. 

PROJECT PHASES:
The project will be implemented along a route developing through the active involvement of the different involved subjects, since its constitutive phase.

· PREPARATORY PHASE 

The preparatory phase of the action will have to be carried out mainly through e.mail contacts between the partners. More specifically, the tasks to be carried during the period preceding the meeting in Frosinone (3 – 4 September 2007) will be the following ones:

· sending to each partner, by the Province of Frosinone, of the questionnaire drafted by the local association of farmers. Each partner will have to accept it and eventually, express remarks and proposals;

· identification, by each partner, of the sample of agricultural farms, to which to submit the questionnaire;

· distribution of the speeches among the partners. These tasks will be coordinated by the Province of Frosinone.

drafting, by each partner, of the speeches in charge of its representatives. These speeches should be , preferably, written also in English, in order to facilitate the translation works

At this stage the Province of Frosinone, in cooperation with its local associations of farmers, has already drafted the questionnaire and translated it into English. The other partners have to translate it from English to their own languages and select the agricultural companies to which to submit it.

 The analysis of data will allow the partners to improve their knowledge of the single agricultural situations and the characteristics  of the involved rural entrepreneurial fabrics, and to foster, trough the comparison which will be realized during the project implementation phase, the exchange of knowledges and the constitution of a common identity.

The final aim is to create an on line data bank.

· PRELIMINARY MEETING – Frosinone (Italy) September 2007(3 – 4)

The preparatory meeting between all the project partners, which will be held in Frosinone, at the seat of the Province of Frosinone, project leader, will last two days.

During the meeting in Frosinone, the speeches will be presented, the exact agenda of the speeches will be decided and the promotion and the publicization of the event in (Hungary or other  East Europe country)will be programmed.

· SEMINAR IN HUNGARY (or other East Europe Country) Period: November 2007

Rate of grant awarded by the European Commission

The Commission has decided to award a grant of € 28.579,60, representing 39,56% of the total eligible costs, excluding the staff costs (€ 9.569,60).

Rate of coo-financing expected from the hosting partner: € 5000,00

Tasks in charge of the partner hosting the seminar involved in the preparation, implementation and follow-up of the measure as well as the dissemination of the results of the measure

A. Partner hosting the seminar:



Preparation of the measure:
· Identification of a local farms sample to which submit the questionnaire drafted by the project leader.

· Participation in the preliminary meeting in Frosinone with two experts and one representative of the institution: definition of the exact content and agenda of the speeches and schedule of  the advertisement of the event in (Hungary); editing and preparation of the documents to be used during the seminar;

· Locals and equipment, subcontracting of an agency for simultaneous interpreting, distribution of the documents to be used during the seminar;
· Identification and selection of the audience;

· promotion and advertisement of the event.

Implementation of the measure:
· Logistic organization: reception, accommodation and local transport for the Italian and Greek guests;

· Attendance of the seminar with two experts and one official representative.


 Follow – up of the measure:  

· Co-ordination of the follow-up of the measure: distribution of the evaluation surveys, assessment and diffusion of their results.

· Posting on its website of a link to the web page given to the event, realized by the project leader (Province of Frosinone).

